## Sheet1
CRS_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CRS_REVIEW_001 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1///Document title | Document title is not correct | it shall be changed to "SAG WEB" | Open
CRS_REVIEW_002 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1//Document Status/Name | name is not correct | it shall be changed to "PO_SAG_CRS_WEB" | Open
CRS_REVIEW_002 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1//Document Status/approvals | "team , mentor and final" approvals are missing | "team , mentor and final" approvals shall be added | Open
CRS_REVIEW_003 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1//Document Status/Author | author name isn't the official name | author name shall be modified to "Ahmed Mohamed" | Open
CRS_REVIEW_004 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1//document history/Date | the date in the document history isn't matching the date of the document status | date shall be updated to the appropriate document creation date | Open
CRS_REVIEW_005 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1//Reference Document/Doc. Name | The Doc. version isn't matching to the version of the referenced Doc | Doc. Name shall be modified to "PO_SAG_CR_WEB" | Open
CRS_REVIEW_006 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 1//Reference Document/version | The Doc. Name isn't matching to the name of the referenced Doc | Doc. version shall be modified to the latest version of the referenced doc. | Open
CRS_REVIEW_007 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 2//project description/definition | The sentnece structure is meaningless, and the it's not describtive. | The Definition shall be for example like that: "The project conists of Website and Dashboard. The Website is for showing our porduct and enable the user the place an order. The Dashboard is for Admin control to show an overview and statistics about the product." | Open
CRS_REVIEW_008 | 2022-10-25 | Ammar Yasser (AM) | V1.0 | 2//Project Description/ Features | points 3 & 4 are details about the project that will be disscussed in later documents | points 3 & 4 shall be removed | Open
Open
Open
Open