## Sheet1
CR_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CR_REVIEW_001 | 2022-10-14 | Esraa Abdelnaby | V1.1 | 1///Document Title | Document Titel not matching Document name. | It shall be as the document name "SAG WEB" | Closed
CR_REVIEW_002 | 2022-10-14 | Esraa Abdelnaby | V1.1 | 1//Table of content/Requiremnts and Mapping | - The forth elemnt in the table of content is not describitive. - The element name dosen't match the section name below | The forth element in the table of content shall be modified to be " Requirments Mapping" instead of "Requirements and Mapping". Match the forth element section name below with the forth element in the table content. | Closed
CR_REVIEW_003 | 2022-10-14 | Esraa Abdelnaby | V1.1 | 1//Document Status/Date | The exited Date related to the previous auther. | Update the Date with the one related to your changes. | Closed
CR_REVIEW_004 | 2022-10-14 | Esraa Abdelnaby | V1.1 | 1//Document Status/Version | Incorrect version | Version shall be V1.2 because the old version was V1.1 | Closed
CR_REVIEW_005 | 2022-10-14 | Esraa Abdelnaby | V1.1 | 1//Document History// | Missing record for the latest auther's changes. | You shall add another row for the new record. This row shall contain the updated version(V1.2), latest auther name(Ahmed Oraby), the latest change date related to the author(09-10-2022), and the change. | Closed
CR_REVIEW_006 | 2022-10-14 | Esraa Abdelnaby | V1.1 | 2//Project Description/ Definition | The sentnece structure is meaningless, and the it's not describtive. | The Definition shall be for example like that: "The project conists of Website and Dashboard. The Website is for showing our porduct and enable the user the place an order. The Dashboard is for Admin control to show an ovweview and statistics about the product." | Closed
CR_REVIEW_007 | 2022-10-15 | Ammar Yasser | V1.1 | 2//Project Description/ Features | points 3 & 4 are details about the project that will be disscussed in later documents | points 3 & 4 shall be removed | Closed
CR_REVIEW_008 | 2022-10-16 | Ammar Yasser | V1.2 | 1//Document Status/author | author name didn't change although the document content has changed | author name shall be changed to the latest author name , in this case "Kottp" | Closed
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open